## KT For GPDPPM
Projects / Knowledge Area | Dataiku Platform | Key information to be transferred | Method of Transfer | Current Resource | Recipient | Timeline | Status | Notes
GPD ALLIANCE PROJECT | https://dss-amer-dev.pfizer.com/projects/GPDPPM_ALLIANCE_PROJECTS/flow/ | GMP and WRD Dashboard Projects 1. Detailed walk through of the flows/ Data Pipeline (ETL). 2. Detailed walk through of Python Code for each flows/ Data Pipeline (ETL). 3. Detailed walk through of jobs being scheduled for each flows/ Data Pipeline (ETL). 4. Understanding of Bussiness Usage/ End User. 5. Basic Domain Knowledge. | Teams call (Recorded Session) | Avinash Gopinath | Sharukh Malik | 2023-09-06 | Completed
GPD_SPA_TRACKER | https://dss-amer-dev.pfizer.com/projects/GPD_SPA_TRACKER/flow/ | Portfolio and Study Data flows. 1. Detailed walk through of the flows/ Data Pipeline (ETL). 2. Detailed walk through of Python Code for each flows/ Data Pipeline (ETL). 3. Detailed walk through of jobs being scheduled for each flows/ Data Pipeline (ETL). 4. Understanding of Bussiness Usage/ End User. 5. Basic Domain Knowledge. | Teams call (Recorded Session) | Avinash Gopinath | Sharukh Malik | 2023-09-07 | Completed
GPD PDA ANALYTICS | https://dss-amer-dev.pfizer.com/projects/GPDPDAANALYTICS/flow/ | PDA Extract Dashboards Project 1. Detailed walk through of the flows/ Data Pipeline (ETL). 2. Detailed walk through of Python Code for each flows/ Data Pipeline (ETL). 3. Detailed walk through of jobs being scheduled for each flows/ Data Pipeline (ETL). 4. Understanding of Bussiness Usage/ End User. 5. Basic Domain Knowledge. | Teams call (Recorded Session) | Avinash Gopinath | Sharukh Malik | 2023-09-07 | Completed
GLB_ALL_DATA_SET | https://dss-amer-dev.pfizer.com/projects/GLBALLDATASET/flow/ | ALLDATA Prod. and ALLDATA Dev. flows. 1. Detailed walk through of the flows/ Data Pipeline (ETL). 2. Detailed walk through of Python Code for each flows/ Data Pipeline (ETL). 3. Detailed walk through of jobs being scheduled for each flows/ Data Pipeline (ETL). 4. Understanding of Bussiness Usage/ End User. 5. Basic Domain Knowledge. | Teams call (Recorded Session) | Avinash Gopinath | Sharukh Malik | 2023-09-08 | Completed
PROD_GBL_DAI_IDASH | https://dss-amer-dev.pfizer.com/projects/GBL_DAI_IDASH/flow/ | Multiple Flows generating Json files. 1. Detailed walk through of the flows/ Data Pipeline (ETL). 2. Detailed walk through of Python Code for each flows/ Data Pipeline (ETL). 3. Detailed walk through of jobs being scheduled for each flows/ Data Pipeline (ETL). 4. Understanding of Bussiness Usage/ End User. 5. Basic Domain Knowledge. | Teams call (Recorded Session) | Avinash Gopinath | Sharukh Malik | 2023-09-11 | Completed
GLB_ONESRC_ETL | https://dss-amer-dev.pfizer.com/projects/GLBONESRCETL/flow/ | Portfolio, Study and Dropped study & project Data flows. 1. Detailed walk through of the flows/ Data Pipeline (ETL). 2. Detailed walk through of Python Code for each flows/ Data Pipeline (ETL). 3. Detailed walk through of jobs being scheduled for each flows/ Data Pipeline (ETL). 4. Understanding of Bussiness Usage/ End User. 5. Basic Domain Knowledge. | Teams call (Recorded Session) | Avinash Gopinath | Sharukh Malik | 2023-09-12
PROD GPD CYCLE TIME METRICS | https://dss-amer-dev.pfizer.com/projects/GPDCYCLETIMEMETRICS/flow/ | CS To FIH, P2P adn Pre-POC project Data flows. 1. Detailed walk through of the flows/ Data Pipeline (ETL). 2. Detailed walk through of Python Code for each flows/ Data Pipeline (ETL). 3. Detailed walk through of jobs being scheduled for each flows/ Data Pipeline (ETL). 4. Understanding of Bussiness Usage/ End User. 5. Basic Domain Knowledge. | Teams call (Recorded Session) | Avinash Gopinath | Sharukh Malik | 2023-09-12
GLB DAI ONESOURCE | https://dss-amer-dev.pfizer.com/projects/GLBDAIONESOURCE/flow/ | OneSource MIrror, PLW Mirror, LOP Daily and LOP Daily STG Data flows. 1. Detailed walk through of the flows/ Data Pipeline (ETL). 2. Detailed walk through of Python Code for each flows/ Data Pipeline (ETL). 3. Detailed walk through of jobs being scheduled for each flows/ Data Pipeline (ETL). 4. Understanding of Bussiness Usage/ End User. 5. Basic Domain Knowledge. | Teams call (Recorded Session) | Avinash Gopinath | Sharukh Malik | 2023-09-13
GPD Forecast Engine | https://dss-amer-dev.pfizer.com/projects/GPDFORECASTENGINE/flow/ | LOP and Scenario main Data flows. 1. Detailed walk through of the flows/ Data Pipeline (ETL). 2. Detailed walk through of Python Code for each flows/ Data Pipeline (ETL). 3. Detailed walk through of jobs being scheduled for each flows/ Data Pipeline (ETL). 4. Understanding of Bussiness Usage/ End User. 5. Basic Domain Knowledge. | Teams call (Recorded Session) | Avinash Gopinath | Sharukh Malik | 2023-09-14

## Description
Column | Description
Key information to be transferred | This column should list the specific areas of knowledge that need to be transferred.
Current Resource | The person or team currently holding the knowledge.
Recipient | The person or team who will receive the knowledge.
Method of Transfer | How the knowledge will be transferred (e.g., training, documentation, mentoring).
Timeline | When the knowledge transfer will take place.
Status | Track the progress of the knowledge transfer (e.g., Not Started, In Progress, Completed).
Notes | Any additional information or context about the knowledge transfer.